## Feuil1
Date | Task | Time spent (hours) | Sub-total | Daily total | Total
2015-10-23 | Created basic project with basic movements (with unity pathfinding) | 0.5 | 0.5 | 3 | 33
| Added ability to target and kill living things | 1 | 1.5
| Enhanced shooting behavior | 0.5 | 2
| Tweaking and fixing fight behaviors | 1 | 3
2015-10-24 | Changed architecture to use classes inheritence + added behavior state machine (coward, agressive and defensive) | 2 | 5 | 5.5
| Basic building mod + integration | 0.5 | 5.5
| Made custom shader and logic to display characters behind walls by transparency | 3 | 8.5
2015-10-25 | Trying to figure out how UI elements work in Unity + designed and integrated HUD (functionnal) | 3.5 | 12 | 9
| Figuring out some other things about the way UI elements work and fixing HUD | 2 | 14
| Added main title menu scene | 0.5 | 14.5
| Fixed some more HUD issues and designed basic map | 1 | 15.5
| Made mission manager, now able to execute (or fail) mission (kill people or persuade them (not tool to persuade yet though) | 2 | 17.5
2015-10-26 | Made minimap (currently without buildings and obstacles) | 2 | 19.5 | 8
| Finished minimap (added buildings and walls blips + rotation) | 2 | 21.5
| Reorganized code and objects hierarchy | 2 | 23.5
| Added wandering behaviour + created civilians | 1 | 24.5
| Working on civilians and bad guys procedular generation (but got unexplained issues so far) | 1 | 25.5
2015-10-27 | Fixed civilians and bad guys generation | 1 | 26.5 | 3.5
| Added defending behaviour | 1 | 27.5
| Fixed some AI behaviours | 0.5 | 28
| Started adding weapons (only hand gun for now) | 1 | 29
2015-10-28 | Added multiple characters control | 1 | 30
| Fixed bugs and reorganized some code | 3 | 33